## Sheet1
RegexDesigner Bugs/Feature Requests
Macros: SortByID/SortByToDo (Ctrl-Shift-I/Ctrl-Shift-T): Run this macro in the bug data to short by ID/To Do
ID | Logged | Title | To Do | Done | Notes
25 | 2002-01-01 | Registration | defer | deferred | Chris will do this
54 | 2002-04-18 | Tooltip group values wrap of too long | defer | deferred
55 | 2002-04-18 | Tooltip disappears after a short period of time | defer | deferred
1036 | 2002-04-17 | Automated build | defer | deferred | Chris will do this
12 | 2002-02-02 | Compile multiple regexes into a single assembly | defer
13 | 2002-02-02 | User should be able to set font and match colors | defer
15 | 2002-02-02 | Regex web service | defer
27 | 2002-01-01 | Show captures in groups | defer
28 | 2002-01-01 | Help should show regex syntax help | defer
29 | 2002-01-01 | Support for boost, VB/COM, JScript, Java and ATL/MFC regexes | defer
31 | 2002-01-01 | Need wrapping back | defer |  | but why?
32 | 2002-01-01 | Codegen screen scraping web service generation | defer
33 | 2002-01-01 | Support for loading test text files for matching from the file system or the web | defer
34 | 2002-01-01 | Regex constructor help, e.g. insert digit, insert letter, group selection, etc. | defer |  | via a context menu and a normal menu
35 | 2002-01-01 | Regex to English parser | defer
36 | 2002-01-01 | Generate possible matches | defer
37 | 2002-01-01 | Extension to built in named regexes in VS.NET for the regex validator control | defer
38 | 2002-01-01 | Toolbar buttons to include easy setting of regex options | defer
39 | 2002-01-01 | Drop down menu of common regexes (http://aspsmith.com/re/) | defer
40 | 2002-01-01 | Continuous matching at regex/toMatch changes | defer
41 | 2002-01-01 | Multiple regexes per project | defer
49 | 2002-04-07 | On Open -> Save -> New -> dirty star flashes then disappears in MainForm caption bar | defer |  | Michael will do this
1005 | 2002-02-16 | Should remove use of files for Navigating to HTML content | defer |  | Use http://discuss.develop.com/archives/wa.exe?A2=ind0202c&L=dotnet&F=&S=&P=13944
1006 | 2002-02-16 | Generate HTML via an XML resource and an XSLT | defer |  | Use http://msdn.microsoft.com/msdnmag/issues/02/03/xml/xml0203.asp
1007 | 2002-01-01 | Integrate as a designer into VS.NET | defer
1014 | 2002-03-15 | drag-n-drop of text in regex and text boxes | defer
1023 | 2002-04-03 | Should use wingdings character instead of @ for empty matches | defer
1026 | 2002-04-05 | Handle Ctrl-Tab and Ctrl-Shift-Tab in txtRegex and txtReplacement Textboxes | defer
1027 | 2002-04-05 | Add regex matching code generation for MC++ and JS.NET | defer
1028 | 2002-04-05 | Serialize last code gen preferences | defer
1029 | 2002-04-05 | Serialize dialog placements | defer
1033 | 2002-04-17 | We need an option specifying to show or hide zero-length matches | defer |  | Default to true and serialized in iso-storage
1034 | 2002-04-17 | We need an option specifying to show or hide non-printing matches | defer
1035 | 2002-04-17 | An icon for each custom file types | defer
1043 | 2002-04-27 | Program menu short cuts should include the help file | defer
44 | 2002-04-07 | Inconsistent code layout in exemplars | drop | dropped | Can't force VB to keep extra spaces on a line
1019 | 2002-03-19 | Whenever regex changes, matches should be cleared | drop | dropped | sometimes need to see what was matched when updated the RE
42 | 2002-01-01 | "The Software Checklist" | dup | dropped
4 | 2002-02-02 | File names with spaces aren't opened when double-clicked | fix | fixed
5 | 2002-02-02 | Doesn't work properly with the Open With dialog | fix | fixed
6 | 2002-02-02 | As form is resized, splitter "wanders" | fix | fixed
7 | 2002-02-02 | Splitter bar hard to select at high resolutions | fix | fixed
8 | 2002-02-02 | Right-to-Left option causes an unhandled exception | fix | fixed
9 | 2002-02-02 | Match count does not match matches shown | fix | fixed | e.g. e* shows yields bunches of empty matches
10 | 2002-02-02 | Tooltips disappear off the right-hand-side | fix | fixed | used title attribute on span to get the job done
11 | 2002-02-02 | Invalid regex exceptions should be caught and shown to the user | fix | fixed | still need a title in the message box that reports the error
14 | 2002-02-02 | Toolbar | fix | fixed
16 | 2002-01-01 | Regex matching code generation for C# and VB.NET | fix | fixed
17 | 2002-01-01 | Replace | fix | fixed
18 | 2002-01-01 | Can leave invalid data in compile options dialog | fix | fixed
19 | 2002-01-01 | Consistent naming, e.g. RegexDesigner, RegexDesigner.NET, Sells Brothers RegexDesigner, etc... | fix | fixed
20 | 2002-01-01 | Window size and arrangement persistence | fix | fixed
21 | 2002-01-01 | User option persistence | fix | fixed | need to do splitter locations and window state, too
22 | 2002-01-01 | MRU for files | fix | fixed
23 | 2002-01-01 | About box | fix | fixed
24 | 2002-01-01 | Help | fix | fixed
26 | 2002-01-01 | Application icon needs to be replaced | fix | fixed | Chris is working with an artist on a new app icon
30 | 2002-01-01 | Split | fix | fixed
43 | 2002-02-06 | Single-match does not work correctly when RightToLeft matching | fix | fixed
45 | 2002-04-07 | Compile to assembly is in wrong location | fix | fixed
46 | 2002-04-07 | Codegen does not handle multiline text expressions | fix | fixed
47 | 2002-04-07 | XSLTCodeGenerator does not appear to be able to handle XML Special Chars | fix | fixed | doh! The template input parameters need XML encoding, e.g. named groups in a regex
48 | 2002-04-07 | Open/Save does not work…Replace text not being saved | fix | fixed
50 | 2002-04-07 | About box typographical error | fix | fixed
51 | 2002-04-07 | Replacement text not cleared/loaded correctly after new/open respectively | fix | fixed
52 | 2002-04-07 | Replacement/Match/Group should be pluralized only if relevant counts > 1 | fix | fixed
53 | 2002-04-16 | Investigate missing @ symbol in the match results for multigroup2.rep? | fix | fixed | "@" symbol displayed in group, but not in results match
56 | 2002-04-18 | Opening help, if missing, yields a very ugly message box too | fix | fixed
1000 | 2002-02-05 | Can't see matches of zero length, e.g. /r/n | fix | fixed | Should show matched control characters, e.g. \r\n in gray
1001 | 2002-02-05 | Need to show groups, by name, if available, in tooltip | fix | fixed | Doh! I had already implemented this functionalty! Where did it go?!?
1002 | 2002-02-06 | When opening a new file, clear the Matched Text region | fix | fixed
1003 | 2002-02-08 | Should clear Match Results when match options change | fix | fixed
1004 | 2002-02-12 | Should remove all reference to _leftControlPercentage | fix | fixed
1008 | 2002-02-18 | Annoying flash as main window is moved at startup | fix | fixed
1009 | 2002-03-03 | Finalize Support Mail body in about box | fix | fixed
1010 | 2002-03-03 | Finalize Sales Mail body in about box | fix | fixed
1011 | 2002-03-03 | Finalize About layout in about box | fix | fixed
1012 | 2002-03-03 | Finalize References layout in about box | fix | fixed
1013 | 2002-03-03 | Fix toolbar button backgrounds | fix | fixed
1015 | 2002-03-18 | Missing app name in title bar | fix | fixed
1016 | 2002-03-18 | /r/n sequences show up on two lines instead of just one, e.g. whitespaces.rep | fix | fixed
1017 | 2002-03-18 | (c) needs to be replaced with © where it occurs | fix | fixed
1018 | 2002-03-18 | All message boxes need consistent, not blank titles | fix | fixed
1020 | 2002-04-01 | When a new project is created, or an existing project is opened, the cursor focus should be set to the Regular Expression textbox. | fix | fixed
1021 | 2002-04-03 | Mixed visiblity matches aren't shown properly | fix | fixed | e.g. MixedVisibilityCharacters.rep
1022 | 2002-04-03 | Multiply-matched CR-LF pairs need to have multiple real CR-LF pairs in matched text | fix | fixed | e.g. MultipleReturns.rep
1024 | 2002-04-05 | Add colorized matches to Replacement string | fix | fixed | See ReplaceText
1025 | 2002-04-05 | Show number of replacement matches | fix | fixed | See ReplaceText
1030 | 2002-04-07 | Update splitting tooltips | fix | fixed
1031 | 2002-04-10 | What's with the underscores in the match results for multigroup2.rep? | fix | fixed | They don't seem like they belong
1032 | 2002-04-14 | The message box that comes up when a file on the command line is not found is hideous | fix | fixed | Please don't show the stack traces to the users
1037 | 2002-04-17 | Excerpt for the Products page | fix | fixed
1038 | 2002-04-17 | Detailed product page | fix | fixed | Just used the most excellent online help
1039 | 2002-04-17 | Installer | fix | fixed
1040 | 2002-04-17 | Saving a read-only file yields a very ugly message box | fix | fixed
1041 | 2002-04-27 | About the authors | fix | fixed | Just need Mike's (although I did enjoy the pictures : )
1042 | 2002-04-27 | Program Menu short cuts should be in Sells Brothers RegexDesigner.NET | fix | fixed | Not two levels of menus, please!
1045 | 2002-04-27 | Help needs to be added as a project to build | fix | fixed
1046 | 2002-04-27 | Setup needs to point at the release version of regexdesigner.exe | fix | fixed
1047 | 2002-04-27 | RegexDesigner.chm needs to be updated on the web site | fix | fixed
1044 | 2002-04-27 | Remove beta marker from about box | fix |  | when we release
1045 | 2002-05-02 | Use red/blue instead of red/green for better contrast when colorizing and for the color blind | fix |  | from Craig
1046 | 2002-05-02 | Check ECMA script causes default re to fail (and lots others) | research |  | from Craig
1047 | 2002-05-02 | Next match/previous match buttons | defer |  | from Craig
1048 | 2002-05-02 | it took me a little while to figure out that spaces were -supposed- to be displayed as @ signs | fix |  | Joel Mueller [jmueller@swiftk.com]
1049 | 2002-05-02 | caused an unhandled exception by pasting the HTML source to http://www.sellsbrothers.com/products/ into the Text To Match box and clicking the Generate Code button | fix |  | Joel Mueller [jmueller@swiftk.com]
1050 | 2002-05-07 | I hate the spaces as @ -- why are we doing this? | fix
1051 | 2002-05-27 | Need to escape & in codegen | fix | fixed | (post v1)
1053 | 2002-05-27 | Replacement patterns don't work | fix |  | e.g. $1, ${name}, $& in Replacement String don't show up in Results window as expanded
1054 | 2002-05-27 | Need support for multiple regexes in a single project | defer
1055 | 2002-05-27 | Need to be able to "see next/prev match" in large hunks of data | fix
1056 | 2002-05-27 | Need Ctrl-A in each text box | fix
1057 | 2002-05-27 | Need to be able to paste large amounts of data into Text to Match | fix
1058 | 2002-05-28 | Have results show *just* the matches | defer |  | jterrell@wans.net
1059 | 2002-05-30 | Should generated MC++ and Java, too | defer |  | Nick Hodapp
1060 | 2002-05-30 | Integrate with RegExLib.com | defer |  | http://regexlib.com/webservices.asmx
1061 | 2002-05-30 | Replace/augment tooltips with treeview to show match/group/capture hierarchy | research